| ACTIVITY-BASED SCHEDULE |  |  |  |
| --- | --- | --- | --- |
| Project Name | AI Learning Environment (working name) |  |  |
| Activity | Duration | Start Date | End Date |
| Phase 1: Initiation | 21 | 8 Sep 2026 | 28 Sep 2026 |
| 1.1 Ideation and research | 21 | 8 Sep 2026 | 28 Sep 2026 |
| Project ideation, name and key users | 7 | 8 Sep 2026 | 14 Sep 2026 |
| Competitor analysis | 7 | 8 Sep 2026 | 14 Sep 2026 |
| Three-project pitch and project selection | 1 | 15 Sep 2026 | 15 Sep 2026 |
| User analysis and business model analysis | 7 | 22 Sep 2026 | 28 Sep 2026 |
| Phase 2: Planning | 15 | 29 Sep 2026 | 13 Oct 2026 |
| 2.1 Planning documents | 14 | 29 Sep 2026 | 12 Oct 2026 |
| Business case, charter, stakeholder analysis and plan | 8 | 29 Sep 2026 | 6 Oct 2026 |
| Requirements, scope, schedules, roles and RACI chart | 10 | 29 Sep 2026 | 8 Oct 2026 |
| User story map, Kanban board and Gantt chart | 7 | 6 Oct 2026 | 12 Oct 2026 |
| 2.2 Final pitch and Vlog 1 | 7 | 7 Oct 2026 | 13 Oct 2026 |
| Pitch preparation and Vlog 1 recording | 6 | 7 Oct 2026 | 12 Oct 2026 |
| Final pitch at Cultivator HQ and Vlog 1 submission | 1 | 13 Oct 2026 | 13 Oct 2026 |
| Phase 3: Design | 22 | 6 Oct 2026 | 27 Oct 2026 |
| 3.1 Prototyping | 13 | 6 Oct 2026 | 18 Oct 2026 |
| Low-fidelity prototype | 4 | 6 Oct 2026 | 9 Oct 2026 |
| High-fidelity prototype in Figma | 9 | 10 Oct 2026 | 18 Oct 2026 |
| 3.2 Usability evaluation | 22 | 6 Oct 2026 | 27 Oct 2026 |
| Usability questionnaire and test tasks | 13 | 6 Oct 2026 | 18 Oct 2026 |
| Usability evaluation session | 1 | 20 Oct 2026 | 20 Oct 2026 |
| Questionnaire analysis and redesign | 7 | 21 Oct 2026 | 27 Oct 2026 |
| 3.3 System architecture | 7 | 21 Oct 2026 | 27 Oct 2026 |
| Architecture and system diagrams | 7 | 21 Oct 2026 | 27 Oct 2026 |
| Phase 4: Fall development | 36 | 27 Oct 2026 | 1 Dec 2026 |
| 4.1 Project setup | 4 | 27 Oct 2026 | 30 Oct 2026 |
| Electron + React project, repository structure and automated checks | 4 | 27 Oct 2026 | 30 Oct 2026 |
| 4.2 Course folders and PDF reader (Aubin) | 7 | 28 Oct 2026 | 3 Nov 2026 |
| Course folder access and course list | 4 | 28 Oct 2026 | 31 Oct 2026 |
| PDF reader with passage selection | 7 | 28 Oct 2026 | 3 Nov 2026 |
| 4.3 AI layer and explanations (Aubin) | 16 | 2 Nov 2026 | 17 Nov 2026 |
| Server proxy and model-independent AI layer | 9 | 2 Nov 2026 | 10 Nov 2026 |
| Page-anchored explanations | 10 | 4 Nov 2026 | 13 Nov 2026 |
| Model picker | 7 | 11 Nov 2026 | 17 Nov 2026 |
| 4.4 Storage, flashcards and quizzes (Chop) | 34 | 28 Oct 2026 | 30 Nov 2026 |
| Local storage and course history | 10 | 28 Oct 2026 | 6 Nov 2026 |
| Flashcard generation and editing | 17 | 4 Nov 2026 | 20 Nov 2026 |
| Quiz generation and marking | 15 | 16 Nov 2026 | 30 Nov 2026 |
| 4.5 Testing and demos | 14 | 18 Nov 2026 | 1 Dec 2026 |
| Accuracy, performance and usability testing of the working app | 13 | 18 Nov 2026 | 30 Nov 2026 |
| Bazaar day work-in-progress demo | 1 | 24 Nov 2026 | 24 Nov 2026 |
| Vlog 2 | 7 | 25 Nov 2026 | 1 Dec 2026 |
| Phase 5: Winter development (tentative) | 66 | 6 Jan 2027 | 12 Mar 2027 |
| 5.1 Accounts and Pro (Chop) | 31 | 6 Jan 2027 | 5 Feb 2027 |
| User accounts | 10 | 6 Jan 2027 | 15 Jan 2027 |
| Pro subscription and payments | 17 | 13 Jan 2027 | 29 Jan 2027 |
| Usage limits | 12 | 25 Jan 2027 | 5 Feb 2027 |
| 5.2 Review and input (Chop and Aubin) | 52 | 6 Jan 2027 | 26 Feb 2027 |
| Text recognition for scanned pages (Aubin) | 17 | 6 Jan 2027 | 22 Jan 2027 |
| Voice input (Aubin) | 19 | 1 Feb 2027 | 19 Feb 2027 |
| Exam dates and spaced review (Chop) | 19 | 8 Feb 2027 | 26 Feb 2027 |
| 5.3 iPad version (Aubin) | 47 | 25 Jan 2027 | 12 Mar 2027 |
| iPad app beta | 47 | 25 Jan 2027 | 12 Mar 2027 |
| Phase 6: Pilot and closing (tentative) | 26 | 15 Mar 2027 | 9 Apr 2027 |
| 6.1 Pilot and release | 26 | 15 Mar 2027 | 9 Apr 2027 |
| Design-partner pilot | 21 | 15 Mar 2027 | 4 Apr 2027 |
| Bug fixes and final release | 14 | 22 Mar 2027 | 4 Apr 2027 |
| Final presentation, capstone showcase and retrospective | 5 | 5 Apr 2027 | 9 Apr 2027 |