| PROJECT CHARTER |  |  |
| --- | --- | --- |
| Project Name | AI Learning Environment (working name) |  |
| Date Produced | 6 October 2026 |  |
| Project Goals | Build a desktop study workspace that teaches from the course files already on a student's device, and test whether it can grow into a self-funded product. The project will: • Remove the repeated setup step: students get AI help on the file they have open, without uploading files or re-explaining the course every session. • Make answers verifiable: every explanation points to the page it came from. • Turn reading into practice: flashcards and quizzes are generated from the same passage, with no manual card-making. • Prove a sustainable model: a free tier on free AI models and a Pro subscription that pays for paid models, so the product can run without outside funding. • Deliver the capstone: meet every ENSE 400 and ENSE 477 deliverable on schedule. |  |
| Project Objectives | Each objective is specific, measurable and dated. The KPI shows how it will be measured. 1. Page-anchored explanations. By 17 November 2026, a student can open a PDF from a local course folder, select a passage and receive an explanation with its page reference. • KPI: 100% of explanations show a page reference; median response time of 10 seconds or less on the free model, across a 20-question test set. 2. Accurate answers. By 24 November 2026, explanations are accurate to the source page. • KPI: at least 85% of 30 sampled explanations rated accurate by the team and two classmates, checked against the page. 3. Practice from the passage. By 1 December 2026, the app generates at least 5 flashcards and a 5-question quiz from a selected passage. • KPI: generation takes 20 seconds or less; at least 80% of generated cards rated correct and useful by testers. 4. Usable by students. Test the prototype with at least 5 students on 20 October 2026, and the working app with at least 5 students by 1 December 2026. • KPI: System Usability Scale (SUS) score of 70 or higher; at least 80% of test tasks completed without help. 5. Less setup time. By 1 December 2026, reduce the time from opening a file to receiving a first useful answer compared with the student's current method (uploading to a general AI assistant). • KPI: at least 50% less time, measured in usability sessions with at least 5 students. 6. Low running cost. Throughout both terms, keep AI spending within the self-funded budget. • KPI: US$0 spent on free-tier requests; paid-model testing at or below US$50. 7. Early adoption and willingness to pay. By the end of ENSE 477 (April 2027), run a pilot with at least 15 design-partner students for at least 3 weeks. • KPI: at least 60% of pilot students active each week; at least 20% say they would pay for Pro. |  |
| Project Budget | Self-funded by the team (bootstrapped). No outside funding. • Paid AI models for testing: up to US$50 across both terms. Free-tier AI models cost US$0. • Hosting, accounts and database: US$0 on free tiers. • Design and code tools: US$0 (Figma education plan, GitHub, VS Code). • Apple Developer Program: US$99 a year, only if the iPad version goes ahead in ENSE 477. Total: up to US$150 over two terms. |  |
| Project Sponsor | Aubin Chriss Izere and Chop Kur, co-founders. The project is self-funded by the team. |  |
| Project Manager | Aubin Chriss Izere and Chop Kur, co-project managers. Project management is shared and the work is split by feature: each member plans, builds and tests the features they own, and both review the schedule and risks together each week. |  |
| Additional Key Project Stakeholders |  |  |
| • Dr. Tim Maciag, ENSE 400/477 instructor: reviews and grades deliverables and runs check-ins and scrums. • Linda, U of R student: interview participant whose problem statement shaped the project. • Design-partner students, U of R classmates: test the app on their own course files and give regular feedback. • ENSE 400 capstone peers: usability testers at the 20 October session and audience at pitches and bazaar day. • Cultivator HQ mentors: audience for the 13 October final pitch; startup and business feedback. • U of R undergraduate students: primary end users. • Graduate and thesis students: secondary end users. • AI model providers (for example Google, Groq, OpenRouter and Anthropic): supply the free and paid models; their pricing, rate limits and terms affect the product. • Course instructors and textbook publishers: own the course materials students study from. |  |  |
| Overall Project Milestones |  | Dates |
| Project idea pitched and selected (complete) |  | 15 Sep 2026 |
| Planning documents complete (Workshop 3); project review and GitHub check-in |  | 6 Oct 2026 |
| Final pitch at Cultivator HQ; Vlog 1 submitted |  | 13 Oct 2026 |
| Low- and high-fidelity prototypes and usability questionnaire ready; usability evaluation session |  | 20 Oct 2026 |
| Usability results analysed; redesign and system architecture done; development starts |  | 27 Oct 2026 |
| Local course folder access and PDF reader with passage selection working |  | 3 Nov 2026 |
| AI explanations with page references and the model picker working |  | 17 Nov 2026 |
| Work-in-progress demo at bazaar day |  | 24 Nov 2026 |
| Flashcards and quizzes working; ENSE 400 scope complete; Vlog 2 submitted |  | 1 Dec 2026 |
| User accounts, Pro subscription and payments (tentative) |  | Late Jan 2027 |
| Spaced review against exam dates and voice input (tentative) |  | Late Feb 2027 |
| iPad version beta; design-partner pilot starts (tentative) |  | Mid Mar 2027 |
| Final release and capstone showcase (tentative) |  | Early Apr 2027 |
| Overall Project Risks |  |  |
| • Free AI tiers change: providers can lower rate limits, change terms or end free access. Free-tier limits are also shared by every student using the team's key. • Privacy: selected passages are sent to outside AI providers, and some free tiers allow prompts to be used to improve their models. This must be disclosed clearly to students. • Wrong answers: AI explanations or page references may be inaccurate. • Unreadable PDFs: scanned or image-only PDFs have no text layer, so passages cannot be selected or sent without text recognition (OCR). • Subscription cost: heavy use of the most expensive models could cost more than a Pro subscription brings in without monthly usage limits. • Scope: accounts, payments, voice input and an iPad version are a lot for a two-person team over two terms. • Team availability: with only two members, illness or other course deadlines can stall a whole feature. • Adoption: students may stay with free tools they already use, such as ChatGPT or NotebookLM. • Copyright: course materials belong to instructors and publishers; the app must send only the selected passage and never store or share course files. |  |  |